## Sheet1
Modules |  | Status | Issue | Comments
AI Writer |  | Working | Model Selection and Credit Allocation
AI Editor |  | Working with Error | Selected Models are not giving results. The generated result is only using default AI model set.
AI Video |  | Working
AI Video to Video |  | Error | Interference Step needs to be Integer and Videi Failed to upload in all modules | Not showing on dashboard
AI Image
| Dall-e3 | Working
| Stable Diffusion | Working
| Midjourney | Error | Check AIML API | Not showing in AI Image
| Flux | Error | Image output is not showing and shows buffering status. Whereas from the backend, the credit is getting deducted | Not showing in AI Image
AI Article Generation |  | Workign with Error | Articles are being generated but it is giving error message when you generate image | Fixed
AI File Chat |  | Upload Fuile Issue | file_get_contents(): Read of 12288 bytes failed with errno=21 Is a directory | Fixed
SEO Tool |  | Error | The Module is not working at all | Fixed
AI Web Chat |  | Error | file_get_contents(): https:// wrapper is disabled in the server configuration by allow_url_fopen=0 https://screenrec.com/share/zGqp5eiT4d | Fixed
AI Chat |  | Working with Error | Model Selection and Credit Allocation | Fixed
AI RSS |  | Error | Not picking up RSS feed . I have used this link https://feeds.bbci.co.uk/news/uk/rss.xml this has worked in the past | Fixed
AI Music |  | Error | Audio Failed to upload | An unexpected error occurred: cURL error 28: Operation timed out after 30001 milliseconds with 0 bytes received (see https://curl.haxx.se/libcurl/c/libcurl-errors.html) for https://api.aimlapi.com/v2/generate/audio/minimax/upload ..... An unexpected error occurred: cURL error 28: Operation timed out after 30000 milliseconds with 0 bytes received (see https://curl.haxx.se/libcurl/c/libcurl-errors.html) for https://api.aimlapi.com/v2/generate/audio/minimax/upload ................... Speaking Audio file is being uploaded. Only music/instrument file not being uploaded. API error
Plaigiarism |  | Error | You need to paste the old code to this before we test | Code has been replaced
Detection |  | Error | You need to paste the old code to this before we test | Code has been replaced
Perplexity |  | Error | Perplexity in Real time chat in AI Chat is not working. Error: | Error fixed. Model is working but API response not coming
Chatbot Training |  | Error | Not picking the website link with the following error: file_get_contents(): https:// wrapper is disabled in the server configuration by allow_url_fopen=0 | Fixed
AI Speech to Text |  | Error | Can't upload the file | Fixed
Gemini API |  |  | models/gemini-pro is not found for API version v1beta, or is not supported for generateContent. Call ListModels to see the list of available models and their supported methods.

## Updated
Modules |  | Status | New Status
AI Writer |  | Working
AI Editor |  | Working
AI Video |  | Working
AI Video to Video |  | Working
AI Image
| Dall-e3 | Working
| Stable Diffusion | Working
| Midjourney | Working
| Flux | Working
AI Article Generation |  | Working
AI File Chat |  | Working
SEO Tool |  | Not working | Fixed but need tokens to test | Non responsive - One error it gave was that it has to be less than 2000 characters.. But the characters were 1000. Please test it in different scenarios. It doesn't work for us | tokens used
AI Web Chat |  | Working
AI Chat |  | Working with Error |  | Real time chat not working https://screenrec.com/share/GeQ3FSMbWx
AI RSS |  | Working
AI Music |  | Not working |  | Try uploading a song. An unexpected error occurred: cURL error 28: Operation timed out after 30001 milliseconds with 0 bytes received (see https://curl.haxx.se/libcurl/c/libcurl-errors.html) for https://api.aimlapi.com/v2/generate/audio/minimax/upload
Plaigiarism |  | Not working | Working | https://screenrec.com/share/7uxYWLsrPV
Detection |  | Not working | Working | https://screenrec.com/share/7uxYWLsrPV
Perplexity |  | Not working |  | Api commands reaching Perplexity but response not coming back from API. Please Fix this.
Chatbot Training |  | Working
AI Speech to Text |  | Working
AI Voice Isolator |  | Working
AI Voice Cloning |  | Not Showing | Working | It is activated and toggled on but not showing on the menu
AI Voiceover |  | Working with error |  | 1: Not showing all Elevenlabs AI models 2: I can also see other users Trained voice models… we sorted this problem our couple of months ago.
Gemini API

## New Updates
SEO Tool | Not working | https://screenrec.com/share/pg2xtRYGBX | tokens used
AI Chat | Working with Error | Real time chat not working https://screenrec.com/share/GeQ3FSMbWx
AI Music | Working with Error | Error as Identified in our call
Perplexity | Not working | Api commands reaching Perplexity but response not coming back from API. Please Fix this.
AI Voiceover | Working with error | 1: Not showing all Elevenlabs AI models 2: I can also see other users Trained voice models… we sorted this problem our couple of months ago.
AI Rewriter | Not working | No response
AI RSS | Working with Error | RSS fetching working fine but it is not generating articles. It was working fine 4 days ago
AI Writer | Not working
I THINK ALL THE WRITING MODELS ARE NOT WORKING AND ADIL IS AWARE OF THAT AND HE PROBABLY IS WORKING ON IT
SMTP Setup |  | Please setup SMTP so the system sends the emails and also we need to test Team invitation which we can't if we don’t have SMTP
Clourflare R2 |  | Please setup Cloudflare R2